## Sheet2
Week No. | Start date | End date | Learning Task | Development task | Status
week 0 |  |  | Understanding project workflow |  | Completed
Week 1 | 2026-05-13 | 2026-05-16 | React Concepts - components, state, routing | Add a simple "Hello [username]" message to the Dashboard. | Completed
Week 1 | 2026-05-17 | 2026-05-19 | Node.js + Express concepts - Middleware,how routers work | Add a GET /api/health/details endpoint that returns the current time and number of users in the DB. | Completed
Week 2 | 2026-05-20 | 2026-05-23 | Learn WebRTC | Build a simple standalone 2-person video call | Completed
Week 2 | 2026-05-24 | 2026-05-26 | Learn fundamentals of socket.io | Add Socket.io to the Server | Completed
Week 3 | 2026-05-27 | 2026-05-29 | Revise database concepts and API | Add DB Table + API | Completed
Week 3 | 2026-05-30 | 2026-06-02 | Revise react concepts | Build the React UI | In progress
Week 4 | 2026-06-07 | 2026-06-10 | - | Build the React UI | In progress
Week 4 | 2026-06-11 | 2026-06-13 |  | Test+Polish | Not started